## Project Management Dashboard
PROJECT MANAGEMENT DASHBOARD
TASK TIMELINE | [7 empty] | TASK TIMELINE
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
TASK | OWNER | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Kick-off | Anna
Set Objectives | Ken
Project Requirements | Sara
Hardware Requirements | James
Finalize Resource Plan | Anna
Investor Presentation | Ken
Staffing | Sara
Construction | James
Alpha Out | Pete
Alpha Testing | Jason
Beta Out | Pete
Beta Testing | Jason
Launch | Pete
Future Planning | Anna
Learn More About Dashboards in Smartsheet

## Project Data
PROJECT MANAGEMENT DATA
TASK TABLE & TIMELINE | [6 empty] | TASK STATUS TRACKING
TASK | OWNER | BEGIN | FINISH | # of DAYS | STATUS |  | STATUS | AMOUNT | %
Kick-off and Topic | Team | 2018-08-23 | 2018-08-30 | 7 | COMPLETE |  | COMPLETE | 3 | 23.08%
Project Abstract | Team | 2018-08-31 | 2018-09-04 | 4 | COMPLETE |  | OVERDUE | 0 | 0%
Project Plan - User Stories/KanbanDashboard | Manoj, Gyanesh | 2018-09-05 | 2018-09-17 | 12 | COMPLETE |  | IN PROGRESS | 2 | 15.38%
High Level Research - Functional | Shalini, Yamini | 2018-09-18 | 2018-09-23 | 5 | COMPLETE |  | NOT STARTED | 8 | 61.54%
High Level Research - Technical | Manoj, Shalini | 2018-09-19 | 2018-09-25 | 6 | COMPLETE
High Level Design Specification | Madhu | 2018-09-20 | 2018-09-26 | 6 | COMPLETE
High Level Proof of Concept End to End | Team | 2018-09-23 | 2018-11-08 | 46 | COMPLETE | [5 empty] | BUDGET
Workbook 1 | Team | 2018-09-23 | 2018-10-03 | 10 | COMPLETE
Research - ML Algorithm and Model | Manoj | 2018-09-23 | 2018-10-25 | 32 | COMPLETE | [5 empty] | PROJECTED | ACTUAL | REMAINDER
Database Design | Shalini, Yamini | 2018-09-28 | 2018-10-20 | 22 | COMPLETE | [5 empty] | 1000000 | 880000 | 120000
Low Level Design Specification | Gyanesh, Madhu | 2018-09-30 | 2018-10-10 | 10 | COMPLETE
Dev Environment Setup - Software/IDE/Database | Team | 2018-10-01 | 2018-10-10 | 9 | COMPLETE
Dep. Env. Setup - GIT/Jenkins/Cloud Infra. | Manoj | 2018-10-02 | 2018-10-06 | 4 | COMPLETE
Workbook 2 | Team | 2018-10-15 | 2018-11-04 | 20 | COMPLETE |  |  |  |  | BUDGET
Data Preparation - Download/Scrape/Curate | Shalini | 2018-09-10 | 2019-01-10 | 122 | IN PROGRESS
Design Specification & Project Contribution | Individual | 2018-10-10 | 2018-11-03 | 24 | NOT STARTED |  |  |  |  | BUDGET
Implement ML model | Manoj | 2018-10-15 | 2019-02-12 | 120 | NOT STARTED
Develop Backend for web application | Madhu | 2018-10-25 | 2019-02-15 | 113 | NOT STARTED | [6 empty] | BUDGET
Develop front end UI for the web application | Yamini | 2018-10-26 | 2019-02-10 | 107 | NOT STARTED
Backend integration with Cloud DB | Gyanesh | 2018-11-03 | 2018-11-15 | 12 | NOT STARTED | [6 empty] | PROJECTED | ACTUAL | REMAINDER
Test web app flow | Team | 2019-01-20 | 2019-02-02 | 13 | NOT STARTED | [6 empty] | 1000000 | 880000 | 120000
MobileApp Development | Shalini | 2019-01-05 | 2019-01-25 | 20 | NOT STARTED
Chrome Plugin Development | Yamini | 2019-01-05 | 2019-01-25 | 20 | NOT STARTED
Deploy ML Model on Cloud | Gyanesh | 2019-01-10 | 2019-01-20 | 10 | NOT STARTED
REST API implementation for ML Model | Manoj | 2019-01-12 | 2019-02-02 | 21 | NOT STARTED
Integrate Web and Mobile App with ML Model | Team | 2019-01-15 | 2019-02-15 | 31 | NOT STARTED
Alexa Skill Dev. and Integration with ML Model | Madhu | 2019-01-25 | 2019-03-01 | 35 | NOT STARTED
Live Stream setup for content monitoring | Manoj | 2019-02-03 | 2019-02-18 | 15 | NOT STARTED
Dashboard Integration | Gyanesh | 2019-02-12 | 2019-02-28 | 16 | NOT STARTED
Integration Testing | Yamini | 2019-02-16 | 2019-03-01 | 13 | NOT STARTED
Functional Testing | Madhu | 2019-02-20 | 2019-03-12 | 20 | NOT STARTED
Model Boosting | Shalini | 2019-03-01 | 2019-03-30 | 29 | NOT STARTED
Project Report | Team | 2019-04-01 | 2019-04-20 | 19 | NOT STARTED
Demo Environment Setup | Team | 2019-04-01 | 2019-04-30 | 29 | NOT STARTED
Demo | Team | 2019-05-01 | 2019-05-15 | 14 | NOT STARTED
RISKS & PENDING ACTIONS
TASK | RISKS |  |  | OPEN |  | PENDING ACTIONS
| HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Kick-off | 1 | 0 | 4 | 2 | 0 | 4
Set Objectives | 2 | 3 | 5 | 1 | 2 | 3
Project Requirements | 3 | 4 | 3 | 2 | 1 | 2
Hardware Requirements | 5 | 8 | 1 | 1 | 0 | 0
Finalize Resource Plan | 8 | 6 | 4 | 0 | 3 | 1
Investor Presentation | 5 | 0 | 0 | 2 | 0 | 2
Staffing | 6 | 4 | 0 | 1 | 2 | 3
Construction | 7 | 3 | 3 | 0 | 1 | 4
Alpha Out | 0 | 2 | 4 | 1 | 3 | 2
Alpha Testing | 4 | 4 | 5 | 2 | 0 | 0
Beta Out | 3 | 6 | 4 | 3 | 2 | 0
Beta Testing | 2 | 3 | 6 | 0 | 1 | 1
Launch | 1 | 1 | 7 | 1 | 0 | 2
Future Planning | 5 | 0 | 2 | 2 | 1 | 3
| 52 | 44 | 48 | 18 | 16 | 27

## Sheet1
Project Topic & Kick off
1 | 7d
2018-08-23 | 2018-08-30
Project Abstract |  | High Level Research Functional & Technical |  | Workbook 1 |  | Workbook 2 |  |  |  | Integrate Web & Mobile
2 | 4d | 4 | 7d | 9 | 10d | 12 | 20d |  |  | 22 | 31d
2018-08-31 | 2018-09-04 | 2018-09-18 | 2018-09-25 | 9/23/2018 | 2018-10-03 | 2018-10-15 | 2018-11-04 |  |  | 2019-01-15 | 2019-02-15
Project Plan |  | High Level Design |  | Dev Environment Setup Software/IDE/Database |  | Develop front end
3 | 12d | 5 | 6d | 10 | 10d | 13 | 107d |  |  | Dashboard integration
2018-09-05 | 2018-09-17 | 2018-09-20 | 2018-09-26 | 2018-10-01 | 2018-10-10 | 2018-10-26 | 2019-02-10 |  |  | 23 | 16d
[10 empty] | 2019-02-12 | 2019-02-28
|  | High Level Proof of Concept End to End |  | Deployment Environment Setup |  | Develop back end
|  | 6 | 7d | 11 | 4d | 14 | 113d
|  | 2018-09-23 | 2018-11-08 | 2018-10-02 | 2018-10-06 | 2018-10-25 | 2019-02-15 | Chrome plugin devpt |  | Integration Testing
[8 empty] | 20 | 20d | 24 | 13d
|  | Research - ML Algorithm and Model |  |  |  | Data preperation |  | 2019-01-05 | 2019-01-25 | 2019-02-16 | 2019-03-01
|  | 7 | 32d |  |  | 16 | 122d
|  | 2018-09-23 | 2018-10-25 |  |  | 2018-09-10 | 2019-01-10
[8 empty] | Alexa skill development |  | Functional Testing
|  | Database Design |  |  |  | Implement ML model |  | 21 | 35d | 25 | 20d
|  | 8 | 22d |  |  | 15 | 120d | 2019-01-25 | 2019-03-01 | 2019-02-20 | 2019-03-12
|  | 2018-09-28 | 2018-10-20 |  |  | 2018-10-15 | 2019-02-12
[6 empty] | Mobile App development |  |  |  | Model Boosting
[6 empty] | 17 | 20d |  |  | 26 | 30d
[6 empty] | 2019-01-05 | 2019-01-25 |  |  | 2019-03-01 | 2019-03-30
[6 empty] | Deploy ML model on cloud |  |  |  | Demo Environment Setup
[6 empty] | 19 | 10d |  |  | 27 | 30d
[6 empty] | 2019-01-10 | 2019-01-20 |  |  | 2019-04-01 | 2019-04-30
Rest API for ML model
[6 empty] | 18 | 20d
[6 empty] | 2019-01-12 | 2019-02-10
[8 empty] | Project Report |  | Demo
[8 empty] | 28 | 20d | 29 | 30d
[8 empty] | 2019-04-01 | 2019-04-20 | 2019-05-01 | 2019-05-15

## Tasks
Models
Yamini: Mobile App and model API for fake image detection | Fake image
Gyanesh: Chrome Plug-in + Model APIs | Stance
Shalini: Model API + Twitter stream + Dashboard | Clickbait
Manoj: Web + Content analysis + Model APIs, Integration | Toxicity
Madhu: IoT + Alexa + Model
Fake image