## Project Management Dashboard
PROJECT MANAGEMENT DASHBOARD
TASK TIMELINE
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
TASK | OWNER | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Kick-off | Anna
Set Objectives | Ken
Project Requirements | Sara
Hardware Requirements | James
Finalize Resource Plan | Anna
Investor Presentation | Ken
Staffing | Sara
Construction | James
Alpha Out | Pete
Alpha Testing | Jason
Beta Out | Pete
Beta Testing | Jason
Launch | Pete
Future Planning | Anna
Learn More About Dashboards in Smartsheet

## Project Data
PROJECT MANAGEMENT DATA
TASK TABLE & TIMELINE | [6 empty] | TASK STATUS TRACKING
TASK | OWNER | BEGIN | FINISH | # of DAYS | STATUS |  | STATUS | AMOUNT | %
Kick-off and Topic | Team | 2018-08-23 | 2018-08-30 | 7 | COMPLETE |  | COMPLETE | 3 | 21.43%
Project Abstract | Team | 2018-03-06 | 2018-03-07 | 1 | COMPLETE |  | OVERDUE | 1 | 7.143%
Workbook 1 | Team | 2018-03-07 | 2018-03-08 | 1 | IN PROGRESS |  | IN PROGRESS | 2 | 14.29%
Workbook 2 | Team | 2018-03-08 | 2018-03-26 | 18 | NOT STARTED |  | NOT STARTED | 8 | 57.14%
Design Spec | Team | 2018-03-10 | 2018-03-11 | 1 | NOT STARTED
Report | Team | 2018-03-11 | 2018-03-12 | 1 | NOT STARTED
Environment Setup | Manoj | 2018-03-12 | 2018-03-17 | 5 | NOT STARTED |  | BUDGET
Architecture & POC | Manoj | 2018-03-17 | 2018-03-18 | 1 | NOT STARTED
Data Prep for ML Model | Manoj | 2018-03-19 | 2018-03-26 | 7 | NOT STARTED |  | PROJECTED | ACTUAL | REMAINDER
ML Model for Feature Detection | Manoj | 2018-03-26 | 2018-04-09 | 14 | NOT STARTED |  | 1000000 | 880000 | 120000
API Development | Manoj | 2018-04-09 | 2018-04-21 | 12 | NOT STARTED
Chrome AddOn App Development | Manoj | 2018-04-21 | 2018-04-24 | 3 | NOT STARTED
Web App Development | Manoj | 2018-03-26 | 2018-04-26 | 31 | NOT STARTED
MobileApp Development |  |  |  |  | NOT STARTED
Alexa Skill |  |  |  |  | NOT STARTED
Live Stream setup for content monitoring |  |  |  |  | NOT STARTED
Dashboard |  |  |  |  | NOT STARTED
IOT integration |  |  |  |  | NOT STARTED
Integration end to end |  |  |  |  | NOT STARTED
Model Boosting |  |  |  |  | NOT STARTED
Testing |  |  |  |  | NOT STARTED
Demo | Manoj | 2018-04-26 | 2019-03-30 | 338 | NOT STARTED
RISKS & PENDING ACTIONS
TASK | RISKS |  |  | OPEN |  | PENDING ACTIONS
| HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Kick-off | 1 | 0 | 4 | 2 | 0 | 4
Set Objectives | 2 | 3 | 5 | 1 | 2 | 3
Project Requirements | 3 | 4 | 3 | 2 | 1 | 2
Hardware Requirements | 5 | 8 | 1 | 1 | 0 | 0
Finalize Resource Plan | 8 | 6 | 4 | 0 | 3 | 1
Investor Presentation | 5 | 0 | 0 | 2 | 0 | 2
Staffing | 6 | 4 | 0 | 1 | 2 | 3
Construction | 7 | 3 | 3 | 0 | 1 | 4
Alpha Out | 0 | 2 | 4 | 1 | 3 | 2
Alpha Testing | 4 | 4 | 5 | 2 | 0 | 0
Beta Out | 3 | 6 | 4 | 3 | 2 | 0
Beta Testing | 2 | 3 | 6 | 0 | 1 | 1
Launch | 1 | 1 | 7 | 1 | 0 | 2
Future Planning | 5 | 0 | 2 | 2 | 1 | 3
| 52 | 44 | 48 | 18 | 16 | 27